## Job Index
[19 empty] | DECK | Before Docking / Sailing or Anchor | 1 | SHIP-YARD | PENDING APPROVAL | PENDING | K1910 | Docking Expenses and General Services | YES
[17 empty] | Estimated Total Spares/Stores Cost | 0 | ENGINE | Before Docking / Anchor | 2 | SHIP-STAFF | P.O. ISSUED | PARTIAL | K1911 | Docking Owners Work | NO
[17 empty] | Estimated Total Services Cost | 0 | ELECT. | During Docking | 3 | 3RD PARTY SERV. | P.I. RECEIVED | COMPLETED | K1912 | Docking Paint
[19 empty] | GENERAL | After Docking / Anchor | 4 | YARD / CREW | INVOICE BOOKED | CANCELLED | K1913 | Docking Anodes
[19 empty] | DOCKING | After Docking / Sailing | 5 | SERV. / YARD | P.I. PAID | MANDATORY | K1914 | Docking seals and Packing
[21 empty] | 6 | CREW / SERV. | AWAITING READINESS | N/A | K1915 | Docking Agency Disbursements
[21 empty] | 7 | YARD / CREW / SERV. | SHIPPED |  | K1916 | Docking Service Engineer's Cost
|  |  |  | Please enter Vessel Name in the PREAMBLE | [18 empty] | RECEIVED |  | K1917 | Docking Slop Disposal
|  |  | VESSEL | Vessel Name |  |  | DOCKING YEAR | 2026-05-21 17:45 |  | DOCKING YARD | [12 empty] | SERVICE CONFIRMED |  | K1918 | Docking Class/Survey Fee
[23 empty] | SERVICE COMPLETED |  | K1919 | Docking Spares/Stores
INDEX FOR DRY DOCK JOBS | [22 empty] | CREDIT TERMS |  | K1920 | Docking Deviation
[6 empty] | Update on spec sheet |  | Update on this sheet | Update on this sheet | [13 empty] | N/A
Sl. | Mandatory Job | REQD. | DEPT. | OFFICE | SPEC No. | JOB STATUS | DESCRIPTION | TIMING | RESPONSIBILITY | SPARES P.O. NUMBER | SPARES P.O. STATUS | EST. SPARES COST | SERVICE P.O. NUMBER | SERVICE P.O. STATUS | EST. SERVICE COST | ACCOUNT CODE | ACCOUNT DESCRIPTION | REMARKS
1 | YES | YES | GENERAL | 100 |  | MANDATORY | PREAMBLE | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 | K1910 | Docking Expenses and General Services
2 | YES | YES | GENERAL | 110 |  | MANDATORY | Standard Rates and Tariffs | During Docking | SHIP-YARD | NA | N/A | 0 | NA | N/A | 0 | K1910 | Docking Expenses and General Services
3 | YES | YES | DECK | 120 |  | MANDATORY | Steel Outfitting on Deck - Standard Structures for Owner's requirement | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 | K1910 | Docking Expenses and General Services
4 | YES | YES | DOCKING | 200 |  | PENDING | Docking General | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 | K1910 | Docking Expenses and General Services
5 | YES | YES | GENERAL | 210 |  | PENDING | Deslopping and Demucking | Before Docking / Anchor | CREW / SERV. | N/A | N/A | 0 | ## | PENDING APPROVAL | 0 | K1911 | Docking Owners Work
6 | YES | YES | DOCKING | 220 |  | PENDING | Cleaning Before Departure | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 | K1912 | Docking Paint
7 | YES | YES | DECK | 405 |  | PENDING | Hull Cleaning, Blasting & Painting | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 | K1913 | Docking Anodes
8 | YES | YES | DECK | 406 |  | PENDING | Hull Marking | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 | K1914 | Docking seals and Packing
9 | NO | NO | DECK | 411 |  | CANCELLED | Ship's Name Bead Welding at 3 locations on the outer hull ** | During Docking | SHIP-STAFF | N/A | N/A | 0 | N/A | N/A | 0 | K1915 | Docking Agency Disbursements
10 | YES | YES | DECK | 415 |  | PENDING | Anchor with Chain Ranging, Washing, Gauging and Maintenance | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 | K1911 | Docking Owners Work
11 | YES | YES | DECK | 416 |  | PENDING | Chain Locker Maintenance | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 | K1911 | Docking Owners Work
12 | YES | YES | DECK | 420 |  | PENDING | Propeller MRO & Survey | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 | K1916 | Docking Service Engineer's Cost
13 | YES | YES | DECK | 425 |  | PENDING | Rope Guard - MRO | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 | K1917 | Docking Slop Disposal
14 | NO | YES | ENGINE | 435 |  | PENDING | Bow Thruster Blade and Tunnel ** | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 | K1918 | Docking Class/Survey Fee
15 | NO | NO | DECK | 436 |  | CANCELLED | Bow Thruster - MRO ** | During Docking | SERV. / YARD | N/A | N/A | 0 | N/A | N/A | 0 | K1919 | Docking Spares/Stores
16 | YES | YES | DOCKING | 440 |  | PENDING | Docking Plugs | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 | K1920 | Docking Deviation
17 | YES | YES | DECK | 445 |  | PENDING | Sea Chest and Sea Chest Grating Maintenance | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 | K1919 | Docking Spares/Stores
18 | YES | YES | DOCKING | 450 |  | PENDING | Rudder Inspection | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
19 | YES | YES | DECK | 505 |  | PENDING | Main Deck - Blasting and Painting ** | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
20 | YES | YES | DECK | 575 (1) |  | PENDING | Ship-side Valves MRO - Forecastle | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
21 | NO | NO | DECK | 575 (2) |  | PENDING | Ship-side Valves MRO - Pump Room ** | During Docking | YARD / CREW / SERV. | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
22 | YES | YES | DECK | 605 |  | PENDING | Pressure Test of Cargo Pipelines on Deck | During Docking | YARD / CREW | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
23 | YES | YES | DECK | 610 |  | PENDING | Pressure Test of Cargo and Bunker Manifold Valves | Before Docking / Sailing or Anchor | SHIP-STAFF | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
24 | YES | NO | DECK | 615 (1) |  | PENDING | Pressure Test of Cargo Tank Heating Coils | Before Docking / Sailing or Anchor | YARD / CREW | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
25 | YES | YES | DECK | 615 (2) |  | PENDING | Pressure Test of Deck Heaters | Before Docking / Sailing or Anchor | YARD / CREW | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
26 | YES | YES | DECK | 615 (3) |  | PENDING | Leak Test of Steam Pipelines (with branches) on Deck | Before Docking / Sailing or Anchor | SHIP-STAFF | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
27 | YES | YES | DECK | 615 (4) |  | PENDING | Pressure Test of Fire and Foam Lines | Before Docking / Sailing or Anchor | SHIP-STAFF | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
28 | YES | YES | DECK | 615 (5) |  | PENDING | Pressure Test of Bunker Pipelines on Deck | During Docking | YARD / CREW | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
29 | NO | NO | DECK | 630 (1) |  | PENDING | Cargo Tank Domes and Closing Gear MRO ** | During Docking | YARD / CREW | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
30 | YES | NO | DECK | 630 (2) |  | PENDING | Cargo Tank Hatch Cover Packing Inspection and / or Renewal | During Docking | SHIP-STAFF | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
31 | NO | YES | DECK | 630 (3) |  | PENDING | 3 | During Docking | YARD / CREW | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
32 | YES | YES | DECK | 630 (4) |  | PENDING | Cargo Tank Butterworth Hatch Covers' Packing Inspection and / or Renewal | During Docking | SHIP-STAFF | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
61.5775 | NO | YES | DECK | 640 (1) |  | PENDING | Windlass Gypsy / Cable Lifter & Winch Structural Maintenance / Repair ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
62.5923 | NO | NO | DECK | 640 (2) |  | PENDING | Windlass or Winch Bearing Rebushing ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
63.6071 | YES | YES | DECK | 640 (3) |  | PENDING | Windlass and Winch Brake Drum & Band Maintenance / Repair | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
64.622 | NO | NO | DECK | 640 (4) |  | PENDING | Windlass and Winch Brake Lining Renewal ** | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
65.6368 | NO | NO | DECK | 645 (1) |  | PENDING | Windlass and Winch Hydraulic Motor MRO ** | During Docking | SERV. / YARD |  |  | 0 |  |  | 0 |  | #N/A
66.6516 | YES | YES | DECK | 645 (2) |  | PENDING | Windlass and Winch Hydraulic Control Block MRO | During Docking | SERV. / YARD |  |  | 0 |  |  | 0 |  | #N/A
33 | YES | YES | DECK | 650 |  | PENDING | P-V Valves MRO | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
67.6664 | YES | YES | DECK |  |  | PENDING | Hose Crane Structural Maintenance | Before Docking / Sailing or Anchor | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
68.6812 | YES | YES | DECK |  |  | PENDING | Hose Crane Hydraulic Hose Renewal | Before Docking / Sailing or Anchor | YARD / CREW / SERV. |  |  | 0 |  |  | 0 |  | #N/A
69.696 | YES | YES | DECK |  |  | PENDING | Hose Crane Hydraulic Control Equipment MRO | During Docking | SERV. / YARD |  |  | 0 |  |  | 0 |  | #N/A
70.7108 | YES | YES | DECK |  |  | PENDING | Hose Crane Wire Renewal | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
71.7256 | NO | NO | DECK |  |  | PENDING | Load Test of Hose Crane / Wire (after renewal) ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
72.7404 | NO | NO | DECK |  |  | PENDING | Scaffolding for Hose Crane Structural MRO ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
73.7552 | NO | NO | DECK |  |  | PENDING | Hose Crane Luffing Hydraulic Cylinder MRO ** | During Docking | SERV. / YARD |  |  | 0 |  |  | 0 |  | #N/A
74.77 | NO | NO | DECK |  |  | PENDING | Provision Crane Structural Maintenance ** | Before Docking / Sailing or Anchor | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
75.7848 | NO | NO | DECK |  |  | PENDING | Provision Crane Wire Renewal ** | During Docking | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
76.7997 | NO | NO | DECK |  |  | PENDING | Load Test of Provision Crane / Wire (after renewal) ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
77.8145 | NO | NO | DECK |  |  | PENDING | Provision Crane Electric / Hydraulic Control Equipment MRO ** | Before Docking / Anchor | CREW / SERV. |  |  | 0 |  |  | 0 |  | #N/A
78.8293 | NO | NO | DECK |  |  | PENDING | Scaffolding for Provision Crane Structural MRO ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
34 | YES | YES | DECK | 660 |  | PENDING | Lifeboat and Rescue Boat removal from vessel and refit | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
79.8441 | YES | NO | DECK |  |  | PENDING | Lifeboat & Rescue Boat Davit Structural Maintenance | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
80.8589 | YES | NO | DECK |  |  | PENDING | Scaffolding for Lifeboat & Rescue Boat Davit Structural MRO | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
81.8737 | NO | NO | DECK |  |  | PENDING | Lifeboat & Rescue Boat Release / Hoisting Gear MRO ** | Before Docking / Anchor | CREW / SERV. |  |  | 0 |  |  | 0 |  | #N/A
82.8885 | NO | NO | DECK |  |  | PENDING | Lifeboat & Rescue Boat Electric Motor MRO ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
83.9033 | NO | NO | DECK |  |  | PENDING | Renewal of Lifeboat and Rescue Boat Falls ** | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
84.9181 | NO | NO | DECK |  |  | PENDING | Load Test of Lifeboat Davits / Boat Falls (after renewal) ** | During Docking | YARD / CREW / SERV. |  |  | 0 |  |  | 0 |  | #N/A
85.9329 | NO | NO | DECK |  |  | PENDING | Load Test and Function Testing of Life Boat(s) and Rescue Boats ** | During Docking | YARD / CREW / SERV. |  |  | 0 |  |  | 0 |  | #N/A
86.9477 | YES | YES | DECK |  |  | PENDING | Lifeboat and Rescue Boat MRO | During Docking | YARD / CREW / SERV. |  |  | 0 |  |  | 0 |  | #N/A
87.9625 | NO | NO | DECK |  |  | PENDING | Freefall Lifeboat Davit Hydraulic Cylinders MRO ** | During Docking | SERV. / YARD |  |  | 0 |  |  | 0 |  | #N/A
88.9774 | NO | NO | DECK |  |  | PENDING | Freefall Lifeboat Davit Hydraulic Pump and HP Piping MRO ** | During Docking | SERV. / YARD |  |  | 0 |  |  | 0 |  | #N/A
89.9922 | NO | NO | DECK |  |  | PENDING | Freefall Lifeboat Hydraulic Winch and Control Block MRO ** | During Docking | SERV. / YARD |  |  | 0 |  |  | 0 |  | #N/A
91.007 | YES | YES | DECK |  |  | PENDING | Life Raft Annual Maintenance / Exchange | Before Docking / Anchor | 3RD PARTY SERV. |  |  | 0 |  |  | 0 |  | #N/A
92.0218 | NO | NO | DECK |  |  | PENDING | Life Raft Cradle Maintenance ** | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
93.0366 | NO | NO | DECK |  |  | PENDING | Life Raft Davit Maintenance, Renewal of Wire, Load Test ** | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
94.0514 | NO | NO | DECK |  |  | PENDING | Accomodation Ladder(s) Removal and Maintenance ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
95.0662 | YES | YES | DECK |  |  | PENDING | Renewal of Accomodation Ladder(s) Wire | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
96.081 | YES | YES | DECK |  |  | PENDING | Accommodation Ladder Air / Electric Winch Motor MRO | Before Docking / Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
97.0958 | YES | YES | DECK |  |  | PENDING | Accommodation Ladder Support and Winch Outfitting MRO | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
98.1106 | NO | NO | DECK |  |  | PENDING | Load Test of Accommodation Ladders' Wire (after renewal) ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
99.1254 | YES | YES | DECK |  |  | PENDING | Renewal of E/Room Hoisting Crane Wire | Before Docking / Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
100.1402 | YES | YES | DECK |  |  | PENDING | Load Test of E/Room Hoisting Crane / Wire (after renewal) | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
101.1551 | YES | YES | DECK |  |  | PENDING | Mast Riser MRO (if fitted) | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
102.1699 | YES | YES | DECK |  |  | PENDING | Mast Riser Valve MRO (if fitted) | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
103.1847 | YES | YES | DECK |  |  | PENDING | P-V Breaker MRO | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
104.1995 | NO | NO | DECK |  |  | PENDING | Maintenance / Repairs to Inert Gas Pipeline Valves ** | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
105.2143 | YES | YES | DECK |  |  | PENDING | IG System Monitoring Equipment on Deck - Inspection, Calibration and MRO | Before Docking / Sailing or Anchor | CREW / SERV. |  |  | 0 |  |  | 0 |  | #N/A
106.2291 | YES | YES | DECK |  |  | PENDING | Deck Water Seal Inspection and MRO | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
107.2439 | YES | YES | DECK |  |  | PENDING | Deck Water Seal SW Supply and O'board Pipeline Inspection, MRO | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
108.2587 | YES | YES | DECK |  |  | PENDING | Deck Water Seal SW O'board Discharge Valve MRO | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
109.2735 | YES | YES | DECK |  |  | PENDING | Calibration of VRL Pressure Sensors (if applicable) | Before Docking / Anchor | 3RD PARTY SERV. |  |  | 0 |  |  | 0 |  | #N/A
110.2883 | NO | NO | DECK |  |  | PENDING | Repairs to Cargo Pipe Sections / Deck Penetration pieces ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
111.3031 | NO | NO | DECK |  |  | PENDING | Removal and Maintenance of Cargo Valves ** | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
112.3179 | NO | NO | DECK |  |  | PENDING | Maintenance / Repairs of Cargo Tank Heating Coils ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
113.3328 | NO | NO | DECK |  |  | PENDING | Maintenance / Repairs of Deck Heaters ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
114.3476 | NO | NO | DECK |  |  | PENDING | Removal and Maintenance of Ballast Valves ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
115.3624 | NO | NO | DECK |  |  | PENDING | Maintenance / Repairs to Gear Actuators for Cargo and IG Valves ** | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
116.3772 | YES | YES | DECK |  |  | PENDING | Repairs to Steam Pipelines (with branches) on Deck | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
117.392 | NO | NO | DECK |  |  | PENDING | Repairs to Fire Line Sections / Bulkhead Penetration pieces ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
118.4068 | YES | YES | DECK |  |  | PENDING | Repairs to Foam line (with branches) on Deck | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
119.4216 | NO | NO | DECK |  |  | PENDING | Repairs to Foam Line Sections / Bulkhead Penetration pieces ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
120.4364 | YES | YES | DECK |  |  | PENDING | Maintenance of Fire Line Isolation Valves & Fire Hydrants | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
121.4512 | YES | YES | DECK |  |  | PENDING | Maintenance of Foam Line Isolation Valves & Foam Hydrants | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
122.466 | YES | YES | DECK |  |  | PENDING | Maintenance of Bunker Pipeline, Valves & Outfitting | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
123.4808 | YES | YES | DECK |  |  | PENDING | Forward Mast Scaffolding | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
124.4956 | NO | NO | DECK |  |  | PENDING | Forward Mast Structural Maintenance ** | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
125.5105 | NO | NO | DECK |  |  | PENDING | Masts on Deck Structural Maintenance ** | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
126.5253 | YES | YES | DECK |  |  | PENDING | Main Mast Scaffolding | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
127.5401 | NO | NO | DECK |  |  | PENDING | Main Mast Structural Maintenance ** | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
128.5549 | YES | YES | DECK |  |  | PENDING | Ship Side Deformed / Wasted Railing Repairs | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
129.5697 | NO | NO | DECK |  |  | PENDING | Cargo Tanks' Coating Repairs ** | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
130.5845 | YES | YES | DECK |  |  | PENDING | Cargo Tanks' Ladders Inspection and Repair (if required) | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
131.5993 | YES | YES | DECK |  |  | PENDING | Cargo Tanks' Bellmouth Inspection and Repair (if required) | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
132.6141 | YES | YES | DECK |  |  | PENDING | Cargo Tanks' Internal Outfitting Inspection and Repair (if required) | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
133.6289 | YES | YES | DECK |  |  | PENDING | Water Ballast Tanks' Internal Outfitting Inspection and Repair (if required) | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
134.6437 | YES | YES | DECK |  |  | PENDING | Water Ballast Tanks' Air Pipe Inspection and Repair | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
135.6585 | YES | YES | DECK |  |  | PENDING | Water Ballast Tanks' Vent Head MRO | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
136.6733 | YES | YES | DECK |  |  | PENDING | Fuel and L.O. Tanks' Air Pipe on Deck Inspection and Repair | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
137.6882 | YES | YES | DECK |  |  | PENDING | Fuel and L.O. Tanks' Vent Head MRO | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
138.703 | NO | NO | DECK |  |  | PENDING | Tank Cleaning Water or FW Tanks' Internal Outfitting Inspection and Repair (if required) ** | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
139.7178 | YES | YES | DECK |  |  | PENDING | FW and Other Misc. Tanks' Air Pipe on Deck Inspection and Repair | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
140.7326 | YES | YES | DECK |  |  | PENDING | FW and Other Misc. Tanks' Vent Head MRO | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
141.7474 | NO | NO | DECK |  |  | PENDING | Funnel Dampers MRO ** | During Docking | YARD / CREW / SERV. |  |  | 0 |  |  | 0 |  | #N/A
142.7622 | NO | NO | DECK |  |  | PENDING | Funnel External Structural Maintenance ** | During Docking | YARD / CREW |  |  | 0 |  |  | 0 |  | #N/A
143.777 | NO | NO | DECK |  |  | PENDING | Funnel External Scaffolding ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
144.7918 | YES | YES | DECK |  |  | PENDING | Funnel Uptake Flame Arrestors - Removal, Refit, MRO | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
26 | NO | YES | ENGINE | 705 |  | PENDING | Main Engine Unit Overhaul ** | Before Docking / Anchor | SHIP-STAFF | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
51.4294 | YES | YES | ENGINE | 710 (1) |  | PENDING | Main Engine Main Bearing inspection & survey | During Docking | YARD / CREW | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
52.4443 | YES | YES | ENGINE | 710 (2) |  | PENDING | Main Engine Crank Pin Bearing inspection & survey | During Docking | YARD / CREW | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
53.4591 | YES | YES | ENGINE | 710 (3) |  | PENDING | Main Engine Cross Head Bearing inspection & survey | During Docking | YARD / CREW | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
54.4739 | YES | YES | ENGINE | 710 (4) |  | PENDING | Main Engine Thrust Bearing and Pad inspection & survey | During Docking | YARD / CREW | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
27 | YES | YES | ENGINE | 713 |  | PENDING | Main Engine Unit Fuel Pumps periodic overhaul | During Docking | SHIP-YARD | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
28 | YES | YES | ENGINE | 714 |  | PENDING | M/E Air Cooler removal & maintenance | During Docking | SHIP-YARD | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
29 | YES | YES | ENGINE | 715 |  | PENDING | Main Engine Turbocharger periodic overhaul | During Docking | 3RD PARTY SERV. | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
30 | NO | NO | ENGINE | 720 |  | PENDING | Aux. Engine Overhaul ** | Before Docking / Sailing or Anchor | SHIP-STAFF | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
31 | NO | YES | ENGINE | 720 |  | PENDING | Aux. Engine Air Cooler cleaning ** | During Docking | SHIP-YARD | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
32 | NO | NO | ENGINE | 720 |  | PENDING | Aux. Engine L.O. Cooler cleaning ** | Before Docking / Sailing or Anchor | SHIP-STAFF | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
33 | NO | NO | ENGINE | 725 |  | PENDING | Aux. Engine Turbocharger overhaul ** | During Docking | 3RD PARTY SERV. | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
34 | YES | YES | ENGINE | 775 |  | PENDING | Ship-side Valves MRO - Engine Room | During Docking | SHIP-YARD | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
55.4887 | NO | YES | ENGINE | 780 (1) |  | PENDING | Tailshaft Removal, Survey & Refit ** | During Docking | SHIP-YARD | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
56.5035 | YES | YES | ENGINE | 780 (2) |  | PENDING | Intermediate Bearing Inspection and Survey | During Docking | SHIP-YARD | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
57.5183 | YES | YES | ENGINE | HEATEX1 |  | CANCELLED | M/E F.O. Heater cleaning & Relief Valve MRO | During Docking | SHIP-YARD | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
59.5479 | YES | YES | ENGINE | PIPE |  | COMPLETED | Repairs to Fire line (with branches) on Deck | During Docking | SHIP-YARD | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
60.5627 | YES | YES | ENGINE |  |  | PENDING | UT Gauging of Ship-side Stub-pieces in Forecastle Store and Pump Room | Before Docking / Sailing or Anchor | 3RD PARTY SERV. |  |  | 0 |  |  | 0 |  | #N/A
145.8066 | YES | YES | ENGINE |  |  | PENDING | Main Engine Sump Tank cleaning & inspection | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
146.8214 | YES | YES | ENGINE |  |  | PENDING | M/E Aux. Blower overhaul & balancing | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
147.8362 | YES | YES | ENGINE |  |  | PENDING | M/E L.O. Cooler maintenance & cleaning | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
148.851 | YES | YES | ENGINE |  |  | PENDING | M/E L.O. Fine-filter maintenance & cleaning | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
149.8659 | YES | YES | ENGINE |  |  | PENDING | M/E L.O. Pumps MRO | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
150.8807 | NO | NO | ENGINE |  |  | PENDING | M/E Exh. Valve L.O. Pumps MRO ** | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
151.8955 | YES | YES | ENGINE |  |  | PENDING | M/E Jacket Cooling Water Cooler maintenance & cleaning | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
152.9103 | NO | NO | ENGINE |  |  | PENDING | M/E J.C.F.W. Pumps MRO ** | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
153.9251 | NO | NO | ENGINE |  |  | PENDING | M/E F.O. Supply Pumps MRO ** | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
154.9399 | NO | NO | ENGINE |  |  | PENDING | M/E F.O. Circulating Pumps MRO ** | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
155.9547 | NO | NO | ENGINE |  |  | PENDING | M/E F.O. Fine-filter (Hot) maintenance & cleaning ** | During Docking | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
156.9695 | YES | YES | ENGINE |  |  | PENDING | M/E F.O. Return Line Back Pressure Reg. Valve MRO | During Docking | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
157.9843 | NO | NO | ENGINE |  |  | PENDING | A/E F.O. Supply Pumps MRO ** | During Docking | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
158.9991 | NO | NO | ENGINE |  |  | PENDING | A/E F.O. Circulating Pumps MRO ** | During Docking | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
160.0139 | NO | NO | ENGINE |  |  | PENDING | A/E F.O. Fine-filter (Hot) maintenance & cleaning ** | During Docking | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
161.0287 | YES | YES | ENGINE |  |  | PENDING | A/E F.O. Return Line Back Pressure Reg. Valve MRO | During Docking | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
162.0436 | YES | YES | ENGINE |  |  | PENDING | A/E F.O. Heater cleaning & Relief Valve MRO | During Docking | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
163.0584 | YES | YES | ENGINE |  |  | PENDING | F.O. Purifier Heater & Relief Valve maintenance | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
164.0732 | YES | YES | ENGINE |  |  | PENDING | Boiler F.O. Heater & Relief Valve maintenance | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
35 | YES | YES | ELECT. | 810 |  | PENDING | Thermal Imaging of all Electrical Panels and SB (in service) | During Docking | SHIP-YARD | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
36 | YES | YES | ELECT. | 815 |  | PENDING | Main Switch Board (MSB) maintenance | During Docking | SHIP-YARD | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
37 | YES | YES | ELECT. | 815 |  | PENDING | Emergency Switch Board (ESB) maintenance | During Docking | SHIP-YARD | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
38 | YES | YES | ELECT. | 816 |  | PENDING | Calibration of MSB and ESB Meters | During Docking | SHIP-YARD | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
39 | YES | YES | ELECT. | 817 |  | PENDING | Reverse Power & Overcurrent Relays inspection and testing | During Docking | SHIP-YARD | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
40 | YES | YES | ELECT. | 818 |  | PENDING | Air Circuit Breakers and Major MCCB maintenance | During Docking | 3RD PARTY SERV. | NA | P.I. RECEIVED | 0 | NA | P.O. ISSUED | 0 |  | #N/A
165.088 | NO | NO | ELECT. |  |  | PENDING | Major Individual Starter Panel maintenance ** | During Docking | SHIP-YARD |  |  | 0 |  |  | 0 |  | #N/A
166.1028 | NO | NO | ELECT. |  |  | PENDING | Various Group Starter Panels maintenance (separate list) ** | Before Docking / Sailing or Anchor | SHIP-STAFF |  |  | 0 |  |  | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 1 |  | PENDING | Emergency Fire Pump Motor overhaul | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
167.1176 | NO | NO | ELECT. | MOTOR 2 |  | PARTIAL | M/E Aux. Blower Motor (Multiple) overhaul & balancing w/Blower ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
168.1324 | NO | NO | ELECT. | MOTOR 3 |  | COMPLETED | E/R Main Blower Motor (Multiple) overhaul & balancing w/Blower ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
169.1472 | NO | NO | ELECT. | MOTOR 4 |  | CANCELLED | Purifier Rm. Blower(s) Motor overhaul & balancing w/Blower ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
170.162 | NO | NO | ELECT. | MOTOR 5 |  | N/A | Pump Rm. Blower Motor (Multiple) overhaul & balancing w/Blower ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
171.1768 | NO | NO | ELECT. | MOTOR 6 |  | PENDING | Forepeak Store Blower Motor overhaul ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
172.1916 | NO | NO | ELECT. | MOTOR 7 |  | PENDING | Steering Gear Rm. Blower Motor overhaul ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
173.2064 | NO | NO | ELECT. | MOTOR 8 |  | PENDING | Various Small Accom. Blowers Motor overhaul (separate list) ** | Before Docking / Sailing or Anchor | SHIP-STAFF | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
174.2213 | NO | NO | ELECT. | MOTOR 9 |  | PENDING | Aux. Boiler FD Fan Motor overhaul & balancing w/Blower ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
175.2361 | NO | NO | ELECT. | MOTOR 10 |  | PENDING | Comp. Boiler FD Fan Motor overhaul & balancing w/Blower ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
176.2509 | NO | NO | ELECT. | MOTOR 11 |  | PENDING | M/E L.O. Pump Motor (Multiple) overhaul ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
177.2657 | NO | NO | ELECT. | MOTOR 12 |  | PENDING | M/E Exhaust Valve L.O. Pump Motor (Multiple) overhaul ** | Before Docking / Sailing or Anchor | SHIP-STAFF | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
178.2805 | NO | NO | ELECT. | MOTOR 13 |  | PENDING | M/E J.C.F.W. Pump Motor (Multiple) overhaul ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
179.2953 | NO | NO | ELECT. | MOTOR 14 |  | PENDING | M/E F.O. Supply Pump Motor (Multiple) overhaul ** | Before Docking / Sailing or Anchor | SHIP-STAFF | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
180.3101 | NO | NO | ELECT. | MOTOR 15 |  | PENDING | M/E F.O. Circulating Pump Motor (Multiple) overhaul ** | Before Docking / Sailing or Anchor | SHIP-STAFF | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
181.3249 | NO | NO | ELECT. | MOTOR 16 |  | PENDING | I.G. Blower Motor (Multiple) overhaul & balancing w/Blower ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
182.3397 | NO | NO | ELECT. | MOTOR 17 |  | PENDING | I.G. Scrubber Water Pump Motor overhaul ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
183.3545 | NO | NO | ELECT. | MOTOR 18 |  | PENDING | Fire Pump Motor (Multiple) overhaul ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
184.3693 | NO | NO | ELECT. | MOTOR 19 |  | PENDING | Main S.W. Pump Motor (Multiple) overhaul ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
185.3841 | NO | NO | ELECT. | MOTOR 20 |  | PENDING | L.T. F.W. Circulating Pump Motor (Multiple) overhaul ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
186.399 | NO | NO | ELECT. | MOTOR 21 |  | PENDING | Main Air Compressor Motor (Multiple) overhaul ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
187.4138 | NO | NO | ELECT. | MOTOR 22 |  | PENDING | HVAC Blower Motor (Multiple) overhaul & balancing w/Blower ** | During Docking | SHIP-YARD | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
188.4286 | NO | NO | ELECT. | MOTOR 23 |  | PENDING | Boiler F.O. Supply Pump Motor (Multiple) overhaul ** | Before Docking / Sailing or Anchor | SHIP-STAFF | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
189.4434 | NO | NO | ELECT. | MOTOR 24 |  | PENDING | Boiler Water Circulating Pump Motor (Multiple) overhaul ** | Before Docking / Sailing or Anchor | SHIP-STAFF | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
190.4582 | NO | NO | ELECT. | MOTOR 25 |  | PENDING | Purifier Motor (Multiple) overhaul ** | Before Docking / Sailing or Anchor | SHIP-STAFF | ## | PENDING APPROVAL | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 26 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 27 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 28 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 29 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 30 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 31 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 32 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 33 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 34 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 35 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 36 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 37 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 38 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 39 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
58.5331 | YES | YES | ELECT. | MOTOR 40 |  | N/A | Motor - Spare Spec | During Docking | SHIP-YARD | N/A | N/A | 0 | N/A | N/A | 0 |  | #N/A
206.6951 | [11 empty] | 0 |  |  | 0 |  | #N/A
207.7099 | [11 empty] | 0 |  |  | 0 |  | #N/A
208.7247 | [11 empty] | 0 |  |  | 0 |  | #N/A
209.7395 | [11 empty] | 0 |  |  | 0 |  | #N/A
210.7544 | [11 empty] | 0 |  |  | 0 |  | #N/A
211.7692 | [11 empty] | 0 |  |  | 0 |  | #N/A
212.784 | [11 empty] | 0 |  |  | 0 |  | #N/A
213.7988 | [11 empty] | 0 |  |  | 0 |  | #N/A
214.8136 | [11 empty] | 0 |  |  | 0 |  | #N/A
215.8284 | [11 empty] | 0 |  |  | 0 |  | #N/A
216.8432 | [11 empty] | 0 |  |  | 0 |  | #N/A
217.858 | [11 empty] | 0 |  |  | 0 |  | #N/A
218.8728 | [11 empty] | 0 |  |  | 0 |  | #N/A
219.8876 | [11 empty] | 0 |  |  | 0 |  | #N/A
220.9024 | [11 empty] | 0 |  |  | 0 |  | #N/A
221.9172 | [11 empty] | 0 |  |  | 0 |  | #N/A
222.9321 | [11 empty] | 0 |  |  | 0 |  | #N/A
223.9469 | [11 empty] | 0 |  |  | 0 |  | #N/A
224.9617 | [11 empty] | 0 |  |  | 0 |  | #N/A
225.9765 | [11 empty] | 0 |  |  | 0 |  | #N/A
226.9913 | [11 empty] | 0 |  |  | 0 |  | #N/A
228.0061 | [11 empty] | 0 |  |  | 0 |  | #N/A
229.0209 | [11 empty] | 0 |  |  | 0 |  | #N/A
230.0357 | [11 empty] | 0 |  |  | 0 |  | #N/A
231.0505 | [11 empty] | 0 |  |  | 0 |  | #N/A
232.0653 | [11 empty] | 0 |  |  | 0 |  | #N/A
233.0801 | [11 empty] | 0 |  |  | 0 |  | #N/A
234.0949 | [11 empty] | 0 |  |  | 0 |  | #N/A
235.1098 | [11 empty] | 0 |  |  | 0 |  | #N/A
236.1246 | [11 empty] | 0 |  |  | 0 |  | #N/A
237.1394 | [11 empty] | 0 |  |  | 0 |  | #N/A
238.1542 | [11 empty] | 0 |  |  | 0 |  | #N/A
239.169 | [11 empty] | 0 |  |  | 0 |  | #N/A
240.1838 | [11 empty] | 0 |  |  | 0 |  | #N/A
241.1986 | [11 empty] | 0 |  |  | 0 |  | #N/A
242.2134 | [11 empty] | 0 |  |  | 0 |  | #N/A
243.2282 | [11 empty] | 0 |  |  | 0 |  | #N/A
244.243 | [11 empty] | 0 |  |  | 0 |  | #N/A
245.2578 | [11 empty] | 0 |  |  | 0 |  | #N/A
246.2726 | [11 empty] | 0 |  |  | 0 |  | #N/A
247.2875 | [11 empty] | 0 |  |  | 0 |  | #N/A
248.3023 | [11 empty] | 0 |  |  | 0 |  | #N/A
249.3171 | [11 empty] | 0 |  |  | 0 |  | #N/A
250.3319 | [11 empty] | 0 |  |  | 0 |  | #N/A
251.3467 | [11 empty] | 0 |  |  | 0 |  | #N/A
252.3615 | [11 empty] | 0 |  |  | 0 |  | #N/A
253.3763 | [11 empty] | 0 |  |  | 0 |  | #N/A
254.3911 | [11 empty] | 0 |  |  | 0 |  | #N/A
255.4059 | [11 empty] | 0 |  |  | 0 |  | #N/A
256.4207 | [11 empty] | 0 |  |  | 0 |  | #N/A
257.4355 | [11 empty] | 0 |  |  | 0 |  | #N/A
258.4503 | [11 empty] | 0 |  |  | 0 |  | #N/A
259.4652 | [11 empty] | 0 |  |  | 0 |  | #N/A
260.48 | [11 empty] | 0 |  |  | 0 |  | #N/A
261.4948 | [11 empty] | 0 |  |  | 0 |  | #N/A
262.5096 | [11 empty] | 0 |  |  | 0 |  | #N/A
263.5244 | [11 empty] | 0 |  |  | 0 |  | #N/A
264.5392 | [11 empty] | 0 |  |  | 0 |  | #N/A
265.554 | [11 empty] | 0 |  |  | 0 |  | #N/A
266.5688 | [11 empty] | 0 |  |  | 0 |  | #N/A
267.5836 | [11 empty] | 0 |  |  | 0 |  | #N/A
268.5984 | [11 empty] | 0 |  |  | 0 |  | #N/A
269.6132 | [11 empty] | 0 |  |  | 0 |  | #N/A
270.628 | [11 empty] | 0 |  |  | 0 |  | #N/A
271.6429 | [11 empty] | 0 |  |  | 0 |  | #N/A
272.6577 | [11 empty] | 0 |  |  | 0 |  | #N/A
273.6725 | [11 empty] | 0 |  |  | 0 |  | #N/A
274.6873 | [11 empty] | 0 |  |  | 0 |  | #N/A
275.7021 | [11 empty] | 0 |  |  | 0 |  | #N/A
276.7169 | [11 empty] | 0 |  |  | 0 |  | #N/A
277.7317 | [11 empty] | 0 |  |  | 0 |  | #N/A
278.7465 | [11 empty] | 0 |  |  | 0 |  | #N/A
279.7613 | [11 empty] | 0 |  |  | 0 |  | #N/A
280.7761 | [11 empty] | 0 |  |  | 0 |  | #N/A
281.7909 | [11 empty] | 0 |  |  | 0 |  | #N/A
282.8057 | [11 empty] | 0 |  |  | 0 |  | #N/A
283.8206 | [11 empty] | 0 |  |  | 0 |  | #N/A
284.8354 | [11 empty] | 0 |  |  | 0 |  | #N/A
285.8502 | [11 empty] | 0 |  |  | 0 |  | #N/A
286.865 | [11 empty] | 0 |  |  | 0 |  | #N/A
287.8798 | [11 empty] | 0 |  |  | 0 |  | #N/A
288.8946 | [11 empty] | 0 |  |  | 0 |  | #N/A
289.9094 | [11 empty] | 0 |  |  | 0 |  | #N/A
290.9242 | [11 empty] | 0 |  |  | 0 |  | #N/A
291.939 | [11 empty] | 0 |  |  | 0 |  | #N/A
292.9538 | [11 empty] | 0 |  |  | 0 |  | #N/A
293.9686 | [11 empty] | 0 |  |  | 0 |  | #N/A
294.9834 | [11 empty] | 0 |  |  | 0 |  | #N/A
295.9983 | [11 empty] | 0 |  |  | 0 |  | #N/A
297.0131 | [11 empty] | 0 |  |  | 0 |  | #N/A
298.0279 | [11 empty] | 0 |  |  | 0 |  | #N/A
299.0427 | [11 empty] | 0 |  |  | 0 |  | #N/A
300.0575 | [11 empty] | 0 |  |  | 0 |  | #N/A
301.0723 | [11 empty] | 0 |  |  | 0 |  | #N/A
302.0871 | [11 empty] | 0 |  |  | 0 |  | #N/A
303.1019 | [11 empty] | 0 |  |  | 0 |  | #N/A
304.1167 | [11 empty] | 0 |  |  | 0 |  | #N/A
305.1315 | [11 empty] | 0 |  |  | 0 |  | #N/A
306.1463 | [11 empty] | 0 |  |  | 0 |  | #N/A
307.1611 | [11 empty] | 0 |  |  | 0 |  | #N/A
308.176 | [11 empty] | 0 |  |  | 0 |  | #N/A
309.1908 | [11 empty] | 0 |  |  | 0 |  | #N/A
310.2056 | [11 empty] | 0 |  |  | 0 |  | #N/A
311.2204 | [11 empty] | 0 |  |  | 0 |  | #N/A
312.2352 | [11 empty] | 0 |  |  | 0 |  | #N/A
313.25 | [11 empty] | 0 |  |  | 0 |  | #N/A
314.2648 | [11 empty] | 0 |  |  | 0 |  | #N/A
315.2796 | [11 empty] | 0 |  |  | 0 |  | #N/A
316.2944 | [11 empty] | 0 |  |  | 0 |  | #N/A
317.3092 | [11 empty] | 0 |  |  | 0 |  | #N/A
318.324 | [11 empty] | 0 |  |  | 0 |  | #N/A
319.3389 | [11 empty] | 0 |  |  | 0 |  | #N/A
320.3537 | [11 empty] | 0 |  |  | 0 |  | #N/A
321.3685 | [11 empty] | 0 |  |  | 0 |  | #N/A
322.3833 | [11 empty] | 0 |  |  | 0 |  | #N/A
323.3981 | [11 empty] | 0 |  |  | 0 |  | #N/A
324.4129 | [11 empty] | 0 |  |  | 0 |  | #N/A
325.4277 | [11 empty] | 0 |  |  | 0 |  | #N/A
326.4425 | [11 empty] | 0 |  |  | 0 |  | #N/A
327.4573 | [11 empty] | 0 |  |  | 0 |  | #N/A
328.4721 | [11 empty] | 0 |  |  | 0 |  | #N/A
329.4869 | [11 empty] | 0 |  |  | 0 |  | #N/A
330.5017 | [11 empty] | 0 |  |  | 0 |  | #N/A
331.5166 | [11 empty] | 0 |  |  | 0 |  | #N/A
332.5314 | [11 empty] | 0 |  |  | 0 |  | #N/A
Note on E9: DC: Update in Sheet 100