## SS Job Selection New
Special Survey Job Selection sheet
Reference | Dry Dock Job List | 1st Special Survey | 2nd Special Survey | 3rd Special Survey | 4th Intermediate Survey | 4th Special Survey | 5th Intermediate Survey | 5th Special Survey
100 | PREAMBLE | Yes | Yes | Yes | Yes | Yes | Yes | Yes
110 | Standard Rates and Tariffs | Yes | Yes | Yes | Yes | Yes | Yes | Yes
120 | Steel Outfitting on Deck - Standard Structures for Owner's requirement | Yes | Yes | Yes | Yes | Yes | Yes | Yes
200 | Docking General | Yes | Yes | Yes | Yes | Yes | Yes | Yes
210 | Deslopping and Demucking | Yes | Yes | Yes | Yes | Yes | Yes | Yes
220 | Cleaning Before Departure | Yes | Yes | Yes | Yes | Yes | Yes | Yes
405 | Hull Cleaning, Blasting & Painting | Yes | Yes | Yes | Yes | Yes | Yes | Yes
406 | Hull Marking | Yes | Yes | Yes | Yes | Yes | Yes | Yes
411 | Ship's Name Bead Welding at 3 locations on the outer hull (if required) ** | No | No | No | No | No | No | No
415 | Anchor with Chain Ranging, Washing, Gauging and Maintenance | Yes | Yes | Yes | Yes | Yes | Yes | Yes
416 | Chain Locker Maintenance | Yes | Yes | Yes | Yes | Yes | Yes | Yes
420 | Propeller MRO & Survey | Yes | Yes | Yes | Yes | Yes | Yes | Yes
425 | Rope Guard - MRO | Yes | Yes | Yes | Yes | Yes | Yes | Yes
435 | Bow Thruster Blade and Tunnel ** | No | No | No | No | No | No | No
436 | Bow Thruster - MRO ** | No | No | No | No | No | No | No
440 | Docking Plugs | Yes | Yes | Yes | Yes | Yes | Yes | Yes
445 | Sea Chest and Sea Chest Grating Maintenance | Yes | Yes | Yes | Yes | Yes | Yes | Yes
450 | Rudder Inspection | Yes | Yes | Yes | Yes | Yes | Yes | Yes
505 | Main Deck - Blasting and Painting ** | No | No | No | No | No | No | No
575_1 | Ship-side Valves MRO - Forecastle | Yes | Yes | Yes | Yes | Yes | Yes | Yes
575_2 | Ship-side Valves MRO - Pump Room (if applicable) ** | No | No | No | No | No | No | No
605 | Pressure Test of Cargo Pipelines on Deck | Yes | Yes | Yes | Yes | Yes | Yes | Yes
610 | Pressure Test of Cargo and Bunker Manifold Valves | Yes | Yes | Yes | Yes | Yes | Yes | Yes
615_1 | Pressure Test of Cargo Tank Heating Coils | Yes | Yes | Yes | Yes | Yes | Yes | Yes
615_2 | Pressure Test of Deck Heaters (if applicable) ** | No | No | Yes | Yes | Yes | Yes | Yes
615_3 | Leak Test of Steam Pipelines (with branches) on Deck | Yes | Yes | Yes | Yes | Yes | Yes | Yes
615_4 | Pressure Test of Fire and Foam Lines | Yes | Yes | Yes | Yes | Yes | Yes | Yes
615_5 | Pressure Test of Bunker Pipelines on Deck | Yes | Yes | Yes | Yes | Yes | Yes | Yes
630_1 | Cargo Tank Domes and Closing Gear MRO ** | No | No | No | No | No | No | No
630_2 | Cargo Tank Hatch Cover Packing Inspection and / or Renewal | Yes | Yes | Yes | Yes | Yes | Yes | Yes
630_3 | Cargo Tank Butterworth Hatch Cover MRO ** | No | No | No | No | No | No | No
630_4 | Cargo Tank Butterworth Hatch Covers' Packing Inspection and / or Renewal | Yes | Yes | Yes | Yes | Yes | Yes | Yes
640_1 | Windlass Gypsy / Cable Lifter & Winch Structural Maintenance / Repair ** | No | No | No | No | No | No | No
640_2 | Windlass or Winch Bearing Rebushing (as necessary) ** | No | No | No | No | No | No | No
640_3 | Windlass and Winch Brake Drum & Band Maintenance / Repair | Yes | Yes | Yes | Yes | Yes | Yes | Yes
640_4 | Windlass and Winch Brake Lining Renewal ** | No | No | No | No | No | No | No
645_1 | Windlass and Winch Hydraulic Motor MRO (as necessary) ** | No | No | No | No | No | No | No
645_2 | Windlass and Winch Hydraulic Control Block MRO | No | Yes | Yes | Yes | Yes | Yes | Yes
650 | P-V Valves MRO | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Hose Crane Structural Maintenance ** | No | Yes | No | Yes | No | Yes | Yes
| Hose Crane Hydraulic Hose Renewal | Yes | Yes | Yes | No | Yes | No | Yes
| Hose Crane Hydraulic Control Equipment MRO | No | Yes | No | Yes | No | Yes | Yes
| Hose Crane Wire Renewal | Yes | Yes | Yes | No | Yes | No | Yes
| Load Test of Hose Crane / Wire (after renewal) ** | Yes | Yes | Yes | No | Yes | No | Yes
| Scaffolding for Hose Crane Structural MRO ** | No | Yes | No | Yes | No | Yes | Yes
| Hose Crane Luffing Hydraulic Cylinder MRO ** | No | Yes | No | Yes | No | Yes | Yes
| Provision Crane Structural Maintenance ** | No | Yes | No | Yes | Yes | Yes | Yes
| Provision Crane Wire Renewal ** | Yes | Yes | Yes | No | Yes | No | Yes
| Load Test of Provision Crane / Wire (after renewal) ** | Yes | Yes | Yes | No | Yes | No | Yes
| Provision Crane Electric / Hydraulic Control Equipment MRO ** | No | Yes | No | Yes | No | Yes | Yes
| Scaffolding for Provision Crane Structural MRO ** | No | Yes | No | Yes | Yes | Yes | Yes
660 | Lifeboat and Rescue Boat removal from vessel and refit | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Lifeboat & Rescue Boat Davit Structural Maintenance | No | Yes | Yes | Yes | Yes | Yes | Yes
| Scaffolding for Lifeboat & Rescue Boat Davit Structural MRO | No | Yes | Yes | Yes | Yes | Yes | Yes
| Lifeboat & Rescue Boat Release / Hoisting Gear MRO ** | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Lifeboat & Rescue Boat Electric Motor MRO ** | No | Yes | No | No | Yes | No | Yes
| Renewal of Lifeboat and Rescue Boat Falls ** | Yes | Yes | Yes | No | Yes | No | Yes
| Load Test of Lifeboat Davits / Boat Falls (after renewal) ** | Yes | Yes | Yes | No | Yes | No | Yes
| Load Test and Function Testing of Life Boat(s) and Rescue Boats ** | Yes | Yes | Yes | No | Yes | No | Yes
| Lifeboat and Rescue Boat MRO | Yes | Yes | Yes | No | Yes | No | Yes
| Freefall Lifeboat Davit Hydraulic Cylinders MRO ** | Yes | Yes | Yes | No | Yes | No | Yes
| Freefall Lifeboat Davit Hydraulic Pump and HP Piping MRO ** | No | Yes | Yes | No | Yes | No | Yes
| Freefall Lifeboat Hydraulic Winch and Control Block MRO ** | No | Yes | Yes | No | Yes | No | Yes
| Life Raft Annual Maintenance / Exchange | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Life Raft Cradle Maintenance ** | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Life Raft Davit Maintenance, Renewal of Wire, Load Test ** | Yes | Yes | Yes | No | Yes | No | Yes
| Accomodation Ladder(s) Removal and Maintenance ** | Yes | Yes | Yes | No | Yes | No | Yes
| Renewal of Accomodation Ladder(s) Wire | Yes | Yes | Yes | No | Yes | No | Yes
| Load Test of Accommodation Ladders' Wire (after renewal) ** | Yes | Yes | Yes | No | Yes | No | Yes
| Accommodation Ladder Air / Electric Winch Motor MRO | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Accommodation Ladder Support and Winch Outfitting MRO | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Renewal of E/Room Hoisting Crane Wire | Yes | Yes | Yes | No | Yes | No | Yes
| Load Test of E/Room Hoisting Crane / Wire (after renewal) | Yes | Yes | Yes | No | Yes | No | Yes
| Mast Riser MRO (if fitted) | No | Yes | Yes | Yes | Yes | Yes | Yes
| Mast Riser Valve MRO (if fitted) | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| P-V Breaker MRO | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Maintenance / Repairs to Inert Gas Pipeline Valves ** | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| IG System Monitoring Equipment on Deck - Inspection, Calibration and MRO | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Deck Water Seal Inspection and MRO | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Deck Water Seal SW Supply and O'board Pipeline Inspection, MRO | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Deck Water Seal SW O'board Discharge Valve MRO | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Calibration of VRL Pressure Sensors (if applicable) | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Repairs to Cargo Pipe Sections / Deck Penetration pieces ** | No | No | No | No | No | No | No
| Removal and Maintenance of Cargo Valves ** | Yes | Yes | Yes | No | Yes | No | Yes
| Maintenance / Repairs of Cargo Tank Heating Coils (as required) ** | No | No | No | No | No | No | No
| Maintenance / Repairs of Deck Heaters (as required) ** | No | No | No | No | No | No | No
| Removal and Maintenance of Ballast Valves (as required) ** | No | No | No | No | No | No | No
| Maintenance / Repairs to Gear Actuators for Cargo and IG Valves ** | No | No | No | No | No | No | No
| Repairs to Steam Pipelines (with branches) on Deck (as required) ** | No | No | No | No | No | No | No
| Repairs to Fire Line Sections / Bulkhead Penetration pieces | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Repairs to Fire and Foam line (with branches) on Deck | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Repairs to Foam Line Sections / Bulkhead Penetration pieces | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Maintenance of Fire Line Isolation Valves & Fire Hydrants | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Maintenance of Foam Line Isolation Valves & Foam Hydrants | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Maintenance of Bunker Pipeline, Valves & Outfitting | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Forward Mast Scaffolding | Yes | Yes | Yes | No | Yes | No | Yes
| Forward Mast Structural Maintenance | Yes | Yes | Yes | No | Yes | No | Yes
| Masts on Deck Scaffolding and Structural Maintenance ** | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Main Mast Scaffolding | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Main Mast Structural Maintenance | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Ship Side Deformed / Wasted Railing Repairs | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Cargo Tanks' Coating Repairs (if required) ** | No | No | No | No | No | No | No
| Cargo Tanks' Ladders Inspection and Repair (if required) ** | No | No | No | No | No | No | No
| Cargo Tanks' Bellmouth Inspection and Repair (if required) | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Cargo Tanks' Internal Outfitting Inspection and Repair (if required) | No | No | No | No | No | No | No
| Water Ballast Tanks' Internal Outfitting Inspection and Repair (if required) | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Water Ballast Tanks' Air Pipe Inspection and Repair | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Water Ballast Tanks' Vent Head MRO | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Fuel and L.O. Tanks' Air Pipe on Deck Inspection and Repair | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Fuel and L.O. Tanks' Vent Head MRO | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Tank Cleaning Water or FW Tanks' Internal Outfitting Inspection and Repair (if required) ** | No | No | No | No | No | No | No
| FW and Other Misc. Tanks' Air Pipe on Deck Inspection and Repair | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| FW and Other Misc. Tanks' Vent Head MRO | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Funnel Dampers MRO ** | No | No | No | No | No | No | No
| Funnel External Structural Maintenance ** | No | No | No | No | No | No | No
| Funnel External Scaffolding ** | No | No | No | No | No | No | No
| Funnel Uptake Flame Arrestors - Removal, Refit, MRO | No | Yes | Yes | No | Yes | No | Yes
705 | Main Engine Unit Overhaul ** | No | No | No | No | No | No | No
710 (1) | Main Engine Main Bearing inspection & survey | Yes | Yes | Yes | Yes | Yes | Yes | Yes
710 (2) | Main Engine Crank Pin Bearing inspection & survey | Yes | Yes | Yes | Yes | Yes | Yes | Yes
710 (3) | Main Engine Cross Head Bearing inspection & survey | Yes | Yes | Yes | Yes | Yes | Yes | Yes
710 (4) | Main Engine Thrust Bearing and Pad inspection & survey | Yes | Yes | Yes | Yes | Yes | Yes | Yes
713 | Main Engine Unit Fuel Pumps periodic overhaul | Yes | Yes | Yes | No | Yes | Yes | No
714 | M/E Air Cooler removal & maintenance | Yes | Yes | Yes | No | Yes | No | Yes
715 | Main Engine Turbocharger periodic overhaul | Yes | Yes | Yes | No | Yes | Yes | No
720 | Aux. Engine Overhaul ** | No | No | No | No | No | No | No
720 | Aux. Engine Air Cooler cleaning ** | No | No | No | No | No | No | No
720 | Aux. Engine L.O. Cooler cleaning ** | No | No | No | No | No | No | No
725 | Aux. Engine Turbocharger overhaul ** | No | No | No | No | No | No | No
775 | Ship-side Valves MRO - Engine Room | Yes | Yes | Yes | Yes | Yes | Yes | Yes
780 (1) | Tailshaft Removal, Survey & Refit ** | No | No | No | No | No | No | No
780 (2) | Intermediate Bearing Inspection and Survey | Yes | Yes | Yes | Yes | Yes | Yes | Yes
HEATEX1 | M/E F.O. Heater cleaning & Relief Valve MRO | Yes | Yes | Yes | No | Yes | Yes | No
PIPE | Repairs to Fire line (with branches) on Deck | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| UT Gauging of Ship-side Stub-pieces in Forecastle Store and Pump Room | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Main Engine Sump Tank cleaning & inspection | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| M/E Aux. Blower overhaul & balancing | Yes | Yes | Yes | No | Yes | No | Yes
| M/E L.O. Cooler maintenance & cleaning | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| M/E L.O. Fine-filter maintenance & cleaning | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| M/E L.O. Pumps MRO | Yes | Yes | Yes | No | Yes | No | Yes
| M/E Exh. Valve L.O. Pumps MRO ** | No | No | No | No | No | No | No
| M/E Jacket Cooling Water Cooler maintenance & cleaning | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| M/E J.C.F.W. Pumps MRO ** | No | No | No | No | No | No | No
| M/E F.O. Supply Pumps MRO ** | No | No | No | No | No | No | No
| M/E F.O. Circulating Pumps MRO ** | No | No | No | No | No | No | No
| M/E F.O. Fine-filter (Hot) maintenance & cleaning ** | No | No | No | No | No | No | No
| M/E F.O. Return Line Back Pressure Reg. Valve MRO | Yes | Yes | Yes | No | Yes | No | Yes
| A/E F.O. Supply Pumps MRO ** | No | No | No | No | No | No | No
| A/E F.O. Circulating Pumps MRO ** | No | No | No | No | No | No | No
| A/E F.O. Fine-filter (Hot) maintenance & cleaning ** | No | No | No | No | No | No | No
| A/E F.O. Return Line Back Pressure Reg. Valve MRO | Yes | Yes | Yes | No | Yes | No | Yes
| A/E F.O. Heater cleaning & Relief Valve MRO | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| F.O. Purifier Heater & Relief Valve maintenance | Yes | Yes | Yes | No | Yes | No | Yes
| Boiler F.O. Heater & Relief Valve maintenance | Yes | Yes | Yes | Yes | Yes | Yes | Yes
810 | Thermal Imaging of all Electrical Panels and SB (in service) | Yes | Yes | Yes | Yes | Yes | Yes | Yes
815 | Main Switch Board (MSB) maintenance | Yes | Yes | Yes | Yes | Yes | Yes | Yes
815 | Emergency Switch Board (ESB) maintenance | Yes | Yes | Yes | Yes | Yes | Yes | Yes
816 | Calibration of MSB and ESB Meters | Yes | Yes | Yes | Yes | Yes | Yes | Yes
817 | Reverse Power & Overcurrent Relays inspection and testing | Yes | Yes | Yes | Yes | Yes | Yes | Yes
818 | Air Circuit Breakers and Major MCCB maintenance | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Major Individual Starter Panel maintenance ** | No | No | No | No | No | No | No
| Various Group Starter Panels maintenance (separate list) ** | No | No | No | No | No | No | No
MOTOR 1 | Emergency Fire Pump Motor overhaul | Yes | Yes | Yes | Yes | Yes | Yes | Yes
MOTOR 2 | M/E Aux. Blower Motor (Multiple) overhaul & balancing w/Blower ** | No | No | No | No | No | No | No
MOTOR 3 | E/R Main Blower Motor (Multiple) overhaul & balancing w/Blower ** | No | No | No | No | No | No | No
MOTOR 4 | Purifier Rm. Blower(s) Motor overhaul & balancing w/Blower ** | No | No | No | No | No | No | No
MOTOR 5 | Pump Rm. Blower Motor (Multiple) overhaul & balancing w/Blower ** | No | No | No | No | No | No | No
MOTOR 6 | Forepeak Store Blower Motor overhaul ** | No | No | No | No | No | No | No
MOTOR 7 | Steering Gear Rm. Blower Motor overhaul ** | No | No | No | No | No | No | No
MOTOR 8 | Various Small Accom. Blowers Motor overhaul (separate list) ** | No | No | No | No | No | No | No
MOTOR 9 | Aux. Boiler FD Fan Motor overhaul & balancing w/Blower ** | No | No | No | No | No | No | No
MOTOR 10 | Comp. Boiler FD Fan Motor overhaul & balancing w/Blower ** | No | No | No | No | No | No | No
MOTOR 11 | M/E L.O. Pump Motor (Multiple) overhaul ** | No | No | No | No | No | No | No
MOTOR 12 | M/E Exhaust Valve L.O. Pump Motor (Multiple) overhaul ** | No | No | No | No | No | No | No
MOTOR 13 | M/E J.C.F.W. Pump Motor (Multiple) overhaul ** | No | No | No | No | No | No | No
MOTOR 14 | M/E F.O. Supply Pump Motor (Multiple) overhaul ** | No | No | No | No | No | No | No
MOTOR 15 | M/E F.O. Circulating Pump Motor (Multiple) overhaul ** | No | No | No | No | No | No | No
MOTOR 16 | I.G. Blower Motor (Multiple) overhaul & balancing w/Blower ** | No | No | No | No | No | No | No
MOTOR 17 | I.G. Scrubber Water Pump Motor overhaul ** | No | No | No | No | No | No | No
MOTOR 18 | Fire Pump Motor (Multiple) overhaul ** | No | No | No | No | No | No | No
MOTOR 19 | Main S.W. Pump Motor (Multiple) overhaul ** | No | No | No | No | No | No | No
MOTOR 20 | L.T. F.W. Circulating Pump Motor (Multiple) overhaul ** | No | No | No | No | No | No | No
MOTOR 21 | Main Air Compressor Motor (Multiple) overhaul ** | No | No | No | No | No | No | No
MOTOR 22 | HVAC Blower Motor (Multiple) overhaul & balancing w/Blower ** | No | No | No | No | No | No | No
MOTOR 23 | Boiler F.O. Supply Pump Motor (Multiple) overhaul ** | No | No | No | No | No | No | No
MOTOR 24 | Boiler Water Circulating Pump Motor (Multiple) overhaul ** | No | No | No | No | No | No | No
MOTOR 25 | Purifier Motor (Multiple) overhaul ** | No | No | No | No | No | No | No
MOTOR 26 | Motor - Spare Spec ** | No | No | No | No | No | No | No
MOTOR 27 | Motor - Spare Spec ** | No | No | No | No | No | No | No
MOTOR 28 | Motor - Spare Spec ** | No | No | No | No | No | No | No
MOTOR 29 | Motor - Spare Spec ** | No | No | No | No | No | No | No
MOTOR 30 | Motor - Spare Spec ** | No | No | No | No | No | No | No